## Sheet1
Project Group (Name/Number): 5
This activity log is for you to document your contributions and ideas you have done towards your final group project. This will be submitted to your instructors along with your project code. You can document how many minutes you spent working on your code, when you had team meetings outside of the class sessions. Or use this as a way to take notes for your own viewing
Name | Week: | Date: | Activity/Task: | Time spent on Activity: | Completed? | Notes:
meeting | 7 | 2022-08-16 | Spoke with the group outside of the session to discuss our ideas. Ideas to use for the project are gym membership database | 30 minutes | Yes | EXAMPLE
Barbara | 1 | 2022-10-07 | research potential project ideas and add to trello board | 3 hrs | Yes | Added to board with potential data set uses, extensions and any areas where we may struggle to meet criteria
Avu | 1 | 2022-10-08 | Added ideas on trello board using recommended projects for beginner programmers | 1 hour |  | Mental health chatbot / CFG revision flashcards with Quizlet API
Helen | 1 | 2022-10-09 | researched fitness tracking data sources and possible data trends | 2hrs | yes | kaggle data set, wythings api
Barbara | 1 | 2022-10-11 | Gothrough project iformation and pull cirteria to match agaist project ideas | 2 hrs | Yes
Barbara | 1 | 2022-10-11 | Create rough project timeline. Cards added to trello baord | 30 min | Yes
meeting | 1 | 2022-10-12 | Had a team meeting before session to discuss ideas and pick a project. We picked fitness applications as our project idea Decided that by next meeting everyone should have the datasets and APIs we need for our project. Delegated different parts of HW 2 to each team member. Added ideas to trello board and made a SWOT board. | 30 min | Yes | Picked our main project idea
Avu | 1 | 2022-10-13 | Shared numerous resources with team on Slack to help with generating ideas. | 30 mins | Yes | Found article on Medium of someone detailing the steps they took to achieve own fitness related analaytics project.
Avu | 1 | 2022-10-13 | Composed and shared document with team on Slack that approaches possible ideas from perspective of how they fulfill each project criteria. Fatima added some of the points to Homework 2. | 1 hr | Yes | Goes through each idea and checks: does it solve a clearly defined problem / provides useful insight into data set that are not obvious to the naked eye etc.
meeting | 1 | 2022-10-13 | Had group meeting after class and made the decision to narrow down our project to look at features of the most popular fitness apps. Defined next steps as focusing on finding more relevant datasets and possibly APIs | 30 mins | Yes | Narrowed question: how the different features of the top thealth and fitness tracking apps (MyFitnessPal/ Fit Bit) enhance 'personalisation' for best customer experience
Fatima | 1 | 2022-10-14 | Researched and collected a range of datasets related to our project for Mondays team meeting. Completed some of H/W 2 | 20 mins | Yes | Posted datasets and APIs to slack group
Avu | 1 | 2022-10-14 | Created a document with possible project questions using the additional data sources team members shared and detailed possible objectives we could achieve with each idea. | 1 hr | Yes | Shared on Slack (Project Qs.docx) - lists out 5 possible project ideas for team to consider and discuss in next meeting.
Fatima | 1 | 2022-10-15 | Found more datasets and narrowed down what to keep for project, added teammates contributions to H/W 2, prepped for Mondays team meeting, listed possible questions for the project. | 1 hr | Yes
Helen |  | 2022-10-16 | Search for datasets and apis for new topic | 4hours | Yes | weather API, ice and temperature csvs historical. machine modelling of wild fire prediction
Barbara | 1 | 2022-10-16 | Search for datasets and apis for agreed topic | 3 hrs | Yes
Meeting | 2 | 2022-10-17 | Group meeting before session | 30 mins | Yes | decided to change projects as we couldn't find suitable public datasets. Agreed to find suitable datasets by tomorrow or decide on a new project
Barbara | 2 | 2022-10-17 | Search for datasets and apis for agreed topic | 3hrs | No | Can find plenty reseacrh papers but little datasets. APIs for fitness trackers are for individual acocunts or software integrations
Barbara | 2 | 2022-10-18 | look at NFT datasets and determine potenial data quality of various data sets and can datasets be merged together | 2 hours | Yes
Fatima | 2 | 2022-10-18 | Researched and found public datasets for NFTs. | 1 hr | Yes | found public NFT datasets on Kaggle about nft sales and history
Helen | 2 | 2022-10-18 | Researched NFTs looked for APIs | 3hours | Yes | Kaggle data and etherscan
Meeting | 2 | 2022-10-18 | Had a group meeting after class with our assigned instructor and suggested new ideas with each other. Group agreed to work on new NFT project idea.
Meeting | 2 | 2022-10-19 | Group meeting: split up tasks between everyone and finished up HW 2 | 1 hr | Yes
Avu | 2 | 2022-10-19 | NFTs were completely new to me so had to spend time researching on educational resources to help me understand what they are and cryptocurrencies. | 1 hr | Yes | Watched Youtube tutorial shared by Fatima on Slack on how Cryptocurrencies work/ Read articles on NFTs, Blockchain + other digital currencies (Blockgeeks.com)
Barbara | 2 | 2022-10-19 | Reviewed cryptocurrenty datasets on yahoo fiance did some explority data and analysis | 4 hrs | Yes
Fatima | 2 | 2022-10-20 | Researched tutorials about visualising with Seaborn heatmap. Made NFT sales visualisation. Finished up H/W 2. group meeting to agree on tasks for tomorrow and discuss visualisation. Split up report between team members | 1.5 hrs | Yes
Barbara | 2 | 2022-10-20 | Further work on exploratory data and start report | 2 hours | Yes
Helen | 2 | 2022-10-20 | Coding API | 6 hour | yes
Avu | 2 | 2022-10-20 | Spent morning working on first draft of NFT visualisations using the datasets shared by Fatima to visualise what they look like pre-cleaning. Spotted outliers and NaN values that would need removing in cleaning process. | 1 hr | Yes | Shared with group on Slack - showed that the 'NFT_Sales.csv' had largest number of outliers and irrelevant columns.
Avu | 2 | 2022-10-20 | Spent evening trying to use QuickNode trial to access their NFT and Web3 APIs. Final stages that required endpoint input requested payment first. | 30 mins | Yes | www.quicknode.com/nft-api
Fatima | 2 | 2022-10-21 | Submit h/w 2 on Github. Start report writing (introduction) | 30 mins | Yes
Fatima | 2 | 2022-10-22 | NFT visualisation and evaluation points | 1.5 hrs | Yes
Fatima | 2 | 2022-10-23 | Report intro draft | 45 mins | Yes
Avu | 2 | 2022-10-23 | Generated questions from produced visualisations relating to NFTs | 30 mins | Yes | eg. How have NFT sales changed since 2017 to 2021? / What are the periods with the highest sales and why? / How CryptoPunks performs in sales against Bored Ape Yacht Club
Meeting | 3 | 2022-10-24 | group meeting after session | 1 hr
Barbara | 3 | 2022-10-24 | Tidy up of yahoo finance analysis and start writing report outcomes | 3 hours | Yes
Barbara | 3 | 2022-10-25 | Tidy up code and add to git hub | 1 hour | Yes
Meeting | 3 | 2022-10-26 | group meet to go through everyones notebooks and talk about presenting + reports | 2 hrs | Yes
Meeting | 3 | 2022-10-27 | meet with Avu to merge notebooks and split NFT tasks | 1.5 hrs | Yes
Barbara | 3 | 2022-10-28 | Finished Question1 analysis on report | 1.5h | Yes
Fatima | 3 | 2022-10-29 | report | 1 hr | Yes
Helen | 3 | 2022-10-29 | Coding API | 6hours | yes
Avu | 3 | 2022-10-29 | Added detailed description of where my data sets where sourced from and how findings from result solve project problem | 1 hr | Yes | Comparative analysis of Bored Apes and Crypto Punks. Highlights the votality of both in sales growth, offering unbiased perspective into project.
helen | 3 | 2022-10-29 | visualisng data | 3 hrs | yes
Meeting | 4 | 2022-10-31 | meet with Barbara to finalise link between Ethereum and NFT sales history | 1 hr | Yes
Avu | 4 | 2022-10-31 | Tackled errors in analysis relating to date values and managed to convert them into datetime from objects. | 30 mins | Yes | BAYC DateTime' & 'CP DateTime' columns.
Barbara | 4 | 2022-10-31 | Assist with code problem for charts | 20 min | Yes
Fatima | 4 | 2022-11-01 | visualise history of sales | 30 mins | Yes
helen | 4 | 2022-11-01 | writing project report | 2.5 hours | yes
Meeting | 4 | 2022-11-01 | Meet to go through each others code and help fix any issues, discussed and finalised main questions | 40 mins | Yes
Barbara | 4 | 2022-11-01 | Rewrote notebook to clean up and streamline analyis and mark up correctly | 2hrs | Yes
Fatima | 4 | 2022-11-02 | fix plot y axis overlapping | 30 mins | Yes
Avu | 4 | 2022-11-02 | Considered Stats measures that could be utilised in my analysis. Using my merged datasets was able to do show the lower and upper quartiles, and median of each data set. | 1.5 hours | Yes | Through measures of central tendency, was able to show how far ahead in sales Bored Apes was against Crypto Punks.
Meeting | 4 | 2022-11-02 | Met up to finalise report points, agreed to complete all code and report writing by tomorrow | 40 mins | Yes
Barbara | 4 | 2022-11-02 | Draft main report sections | 2 hours | Yes
helen | 4 | 2022-11-02 | Finalising and cleaning code | 1.5hours | yes
Fatima | 4 | 2022-11-03 | finalise visualisations in notebook + detailed comments to explain code + merge notebooks + finalise NFT report writing, key findings and conclusions + make Github repo public | 4 hrs | Yes
Barbara | 4 | 2022-11-03 | Merge individual project log to master | 15 mins | Yes
Meeting | 4 | 2022-11-03 | Group meeting to go through final merged notebook + presentation plan + finalise report
Tutor consultation | 4 | 2022-11-03 | Group meeting with Adeola and had opportunity to express final concerns before submission and requested brief review of our merged notebook and report to see if content fulfilled core project objectives & CFG requirements | 40 mins | Yes | Was reassured we are on the right track. Tutor agreed our report was in excess of 7 pages due to the use of multiple graph outputs and that this was ok.
Avu | 4 | 2022-11-04 | Started working on draft presentation slides using report content to summarise possible key points each member could talk about in presentation. Completed part on NFT historical sales. | 1 hour | Yes | Followed process of Who (Crypto Punks and Bored Ape top NFT collections) , What (Their historical sales data), Where (Time periods - of growth and decline) and Why (Show the investment potential during peak sale periods but also highlight their unpredictability during sustained periods of growth). Finished of with personal SWOT analysis of this part of project.
Group | 4 | 2022-11-04 | upload datasets onto Github | 1 hour |  | CSVs
Fatima + Avu | 4 | 2022-11-05 | NFT powerpoint slides
Group | 4 | 2022-11-06 | submit project onto Github , tidy up file, last checks | 2 hour | Yes | Datasets, Project log, Report, Notebook
Total time: